## Title
National Information Exchange Model
NIEM Cost Model v. 2.0 (Medium Participation)
2015-06-23

## Overview
NIEM Cost Model v. 2.0 (Medium Participation)
Overview
Table of Contents
| 1 | Instructions
| 2 | Exchange Variables
| 3 | Cost Variables
| 4 | Activities
| 5 | Analysis
| 6 | Appendix
Introduction
The purpose of this model is to help and assist organizations to understand the true value of NIEM and what costs are associated with it. It will provide value by identifying the quantitative costs that are associated with implementing NIEM into an organization and provides a baseline funding amount needed for implementation.
The model is based on several assumptions and variables which are inputted by the user, and it is an attempt to measure quantifiable elements of the NIEM value proposition. This model has been modified from the original pilot NIEM Cost Model to account for additional costs and variables associated with the NIEM Engagement Process. It takes into account the assumption that an organization will continue to increase the number of exchanges and partners that it will have for the information sharing and exchange initiative.
Moreover, the model takes into account research and discussions that the NIEM Engagement Process team (PMO) has conducted and assessed. This model incorporates not only the costs that are associated with NIEM but also the additional benefits and value of using NIEM in an organization. It also allows for organizations to interact and follow-up with NIEM PMO for future checkpoints and updates on status of the implementation.

## 1.0 Instructions (hidden)
NIEM Cost Model v. 2.0 (Low Participation)
Introduction
Back to Overview
Cost Model Instructions
|  | The Overall Instructions section describes how the cost model is structured and how tabs and cells are colored to indicate their function and if they require user input. The Steps for Completing the Model section provides step-by-step instructions for completing each input tab. The Outputs section describes the outputs generated by the model. | d
Overall Instructions
The Cost Model contains three tabs that require the user to input data and five tabs that generate outputs. To complete the model, enter all required data in the input tabs in sequential order (Exchange Variables, Cost Variables, Activities). Analysis based on these inputs will automatically be generated in the output tabs (Summary Analysis and Base YR - YR3 tabs). The Appendix provides supporting information regarding the formulas and baseline data.
Tab Color Key: Blue tabs require user input, orange tabs contain outputs and should not be manipulated. Font Color Key: Blue text should be updated by the user, green text is default data and should only be updated if appropriate, cells with black text are locked and should not be manipulated.
Default Data: Tabs requiring user input contain pre-populated default data values in green. These default values are derived from averages of actual data gathered from organizations that have implemented NIEM and custom XML exchanges. The default data are intended to provide a baseline, but the actual data for each organization may differ from this baseline. Default values should be replaced with actual values for the organization being assessed wherever appropriate.
Steps to Complete the Cost Model
Exchange Variables: The Exchange Variables tab allows the user to enter variables about the exchange, including: IEPD reuse, number of additional exchanges, exchange complexity, and data element reuse.
1. Enter the number of times the new IEPD will be reused - Specify the number of times that the IEPD developed in the initial effort will be reused by different systems to share information. (Enter for all years known)
2. Enter the number of additional exchanges - Specify the number of individual exchanges/IEPDs that will be developed. (Enter for all years known)
3. Select the strength level of governance -- Select a projected level of the strength of governance (strong, moderate or weak) for developing the NIEM exchange. The level of political goodwill, consensus among stakeholders, leadership capabilities, etc. will affect the exchange complexity and time it takes to complete tasks.
4. Select the number of elements in the exchange - Select a projected number of elements in the exchange (0-50, 50-150, or 150 or more). The number of elements will affect the exchange complexity as more elements require a higher level of effort and more time to complete tasks.
5. Update hours associated with level-of-effort (if appropriate) - The Level-of-Effort table is used to assign hours for completing each task in the Activities tab based on the complexity of the exchange (selected in the Exchange Variables tab) and the Level-of-Effort estimates (from the Activities tab).
6. Adjust the level of integration (if appropriate) - The Level of Integration table accounts for how varying degrees of overlap between data elements for the planned information exchange and existing NIEM data elements will affect development costs. The model makes the baseline assumption that some (<50%) of the elements used in the exchange already exist and have been defined in the NIEM model. If this is not the case, adjust the model for different degrees of overlap by changing the Reuse of NIEM Data Elements variable in the Variables tab. Example: If all the elements in the planned exchange are already defined in NIEM, then the model will subtract 100% of the costs associated with defining terms with exchange partners and building the extension schema for the NIEM exchange. If many (>50%) of the elements exist in NIEM, the model will subtract 50% of the costs associated with these tasks. If no elements already exist in NIEM, the model will increase the costs by 50% for both tasks.
7. Specify if existing IEPD will be reused - Select "YES" if an existing IEPD can be leveraged to develop the new NIEM exchange. When true, the model will subtract some of the costs associated with developing the initial IEPD, but it does not affect the costs associated with additional development efforts.
8. Select the % of existing data elements that will be reused - Estimate the percentage of data elements in the new exchange that already exist in the NIEM data model and select the corresponding drop-down option. This variable is used to adjust the cost of activities related to "Define Terms with Exchange Partner" (Tasks 3.2) and "Create Extension Schema or Entire Schema" (Task 4.2.2). Cost adjustment percentages can be found in the Level of Integration Table in the Cost Variables tab. The actual adjustments are made in the "Discount Factors" section of the Analysis tab.
Cost Variables: The Cost Variables tab allows the user to enter estimated cost variables for developing and implementing the exchange, including: hours associated with levels-of-effort, hourly rates, level of integration, and other additional costs.
1. Update hourly rates and select resource types - The Hourly Rates table is used to calculate dollar values for each task by providing hourly rates for the resource categories. a. Identify the type of resource that will be used for each resource category: internal (agency/organization staff), external (contractors), or blended (both internal and external). b. Update the labor rates as needed to reflect actual hourly rates for internal, external, and blended resources (as applicable).
2. Enter estimated additional costs - In addition to labor costs, the model assumes that there are training, hardware, and software costs associated with developing and implementing an exchange. a. Enter the estimated cost to train resources in NIEM development. While NIEM training courses are offered free of charge, this estimate should reflect the total labor costs for resources to take the training. The default value is based on an estimate of 20 total hours multiplied by a blended hourly rate (Cost Variables - crosspoint between Blended Rate and Average Rate (H19). b. Enter the estimated cost for hardware required for the exchange, such as servers. c. Enter the estimated cost for software required for the exchange.
3. Enter estimated funding amounts - The Funding Amounts are the approved/estimated funding amounts that are associated with Information Sharing and Exchange initiatives. a. Enter the estimated funding for each year for the next 3 years (if known).
4. Enter estimated outreach costs - Joining NIEM defrays any existing outreach costs related to information exchange. User should input the current outreach costs associated with information exchange for the organization.
Activities: The Activities tab allows the user to enter estimated levels of effort for developing an initial NIEM exchange vs a custom exchange. Information exchange development is divided into the six IEPD lifecycle phases and each phase is broken down into individual tasks. Each task may involve six potential resource categories: Engineer, Architect, Technical, Program Management (PM), Business Analyst, and Subject Matter Expert (SME).
1. Assign levels-of-effort - Level-of-effort estimates are used in conjunction with a complexity variable (entered in the Exchange Variables tab) to assign hours to each task in the IEPD lifecycle. This is done by looking up the hours in the level-of-effort table on the Cost Variables tab using the complexity variable and the selected level-of-effort. Levels-of-effort should be entered for two scenarios: 1) developing an initial NIEM exchange and 2) developing a custom exchange. a. Select an estimated level-of-effort (N/A, Low, Medium, or High) for each task and each resource category (columns D-O). If a resource is not expected to participate in a particular task, select N/A. If the estimated level-of-effort is unknown, keep the default value.
2. Update the escalation factors (if appropriate) - Escalation factors account for the reduced level-of-effort needed to develop additional exchanges beyond the initial exchange. The factors are a percentage (0% to 100%) of the initial level-of-effort for each task. As with the levels-of-effort, the escalation factors may vary for NIEM exchanges and custom exchanges. Escalation factors will differ if an organization is developing an exchange for new data as opposed to if the organization is replicating an existing exchange (same data). a. Review the NIEM and Custom escalation factors (columns T-Q) for the development of additional exchanges (beyond the initial exchange) to understand how the cost of additional exchanges will be discounted. b. Update the escalation factors, if appropriate. Changing the escalation factors is not recommended for those who are new to NIEM.
The assumption that the cost of developing NIEM exchanges decreases as you increase the number of exchanges is the foundation of the NIEM value proposition. This is attributed to the experience gained from developing the initial exchange along with opportunities to reuse elements of the original exchange (and other existing in the repository) as well as the potential to save on overhead (such as training). This underlying assumption is conveyed in the cost model as escalation factors for developing exchanges beyond the original information exchange.
Outputs
The model will generate outputs in the Dashboard, Analysis, and Cash Flow tabs based on analysis of the inputs provided in the previous tabs.
Summary Analysis: The Summary Analysis tab gives a comparison of the costs to develop and implement a NIEM exchange vs a Custom exchange over 4 years. This tab along with the yearly analysis tabs can be used to develop a baseline budget for the exchange initiative.
Yearly Analysis: The Yearly Analysis tabs provide: • Itemized recurring costs for the initial NIEM exchange • Itemized recurring costs for additional NIEM exchanges using the same and/or new data • Itemized costs for the Custom exchange for each of the exchanges listed above • Discount factors for IEPD reuse and reuse of data elements • Total Costs for each exchange • Cost comparisons between the NIEM exchange and the Custom exchange by each line item

## 2.0 Exchange Variables
NIEM Cost Model v. 2.0 (Medium Participation)
Exchange Variables
[8 empty] | Strong | 0-50
Back to Overview | [7 empty] | Moderate | 50-150
[8 empty] | Weak | 150 or more
Exchange Factors | [6 empty] | Level of Effort in Hours per Complexity Level
|  | Base Year | Year 1 | Year 2 | Year 3 |  |  | Simple | Moderate | Complicated
IEPD Reuse | Number of additional systems (beyond initial exchange) that will use the information | 1 | 3 | 4 | 5 |  | NA | 0 | 0 | 0
Number of Additional Exchanges | Number of additional exchanges that the organization plans on developing to exchange different data | 0 | 0 | 0 | 0 |  | Low | 16 | 40 | 64
Governance | Political goodwill, strong leadership and project management, and engaged stakeholders | Moderate |  |  |  | 2 | Medium | 32 | 80 | 128
Number of Elements | Number of elements in exchange | 50-150 |  |  |  | 2 | High | 48 | 120 | 192
Exchange Complexity | Complexity of the exchange | Moderate |  |  |  | 2
Term Definition (3.0) and Extension Schema (4.2.2) Escalation Factors
Model Overlap | NIEM
All Elements Already Exist in NIEM | -100%
Many (>50%) Elements Already Exist in NIEM | -50%
Some (<50%) Elements Already Exist in NIEM | -20%
No Elements Already Exist in NIEM | 0%
Discount Factors
Existing IEPD Reuse | Does an IEPD already exist | NO
Reuse of NIEM Data Elements | Number of new elements that do not exist in the NIEM model | Some (<50%) Elements Already Exist in NIEM

## 3.0 Cost Variables
NIEM Cost Model v. 2.0 (Medium Participation)
Cost Variables
Back to Overview | Back to Overview
Hourly Rates
| Title | Internal | External | Type | Rates
Resource Category | Business/Data Analyst | 70.56 | 70.56 | Internal | 70.56
| EDM Architect | 106.53 | 106.53 | Internal | 106.53
| Enterprise Architect | 120.95 | 120.95 | Internal | 120.95
| Programmer | 92.01 | 92.01 | Internal | 92.01
| Project Manager | 98.93 | 98.93 | Internal | 98.93
| Senior Management | 140 | 140 | Internal | 140
| SOA Programmer | 92.01 | 92.01 | Internal | 92.01
| Test Analyst | 58.892 | 58.89 | Internal | 58.892
| Service Lead | 101.79 | 101.79 | Internal | 101.79
| Business Stakeholders | 100 | 0 | Internal | 100
| Average Rate | 163.612 | 146.945 | Internal | 163.612
Other Costs | Cost Type | Base Year | Year 1 | Year 2 | Year 3
| NIEM Training Cost | 6700 | 5000 | 5000 | 5000
| Hardware Cost | 0 | 0 | 0 | 0
| Software Cost | 0 | 0 | 0 | 0
Funding | Amount Type | Base Year | Year 1 | Year 2 | Year 3
| Grants | 0 | 0 | 0 | 0
| General Funding | 0 | 0 | 0 | 0
| Special Funding | 0 | 0 | 0 | 0
| Misc | 0 | 0 | 0 | 0
| Total | 0 | 0 | 0 | 0
Outreach Costs | Additional Discount | Cost
| Community Outreach | 0
| Market Research | 0
| Marketing Material | 0
| Total | 0

## 4.0 Activities
NIEM Cost Model v. 2.0 (Medium Participation)
Activities
Back to Overview
|  |  | Estimated Levels of Effort (Based on Education/Skill Level of FTE) | [9 empty] | Discount Factor
Activity |  |  | Initial NIEM Exchange | [9 empty] | Same Data | New Data
|  |  | Business/Data Analyst | EDM Architect | Enterprise Architect | Programmer | Project Manager | Senior Management | SOA Programmer | Test Analyst | Service Lead | Business Stakeholders | NIEM Escalation | NIEM Escalation
1 | Scenario Planning
| 1.1 | Establish a Vision | NA | NA | NA | NA | NA | Medium | NA | NA | High | NA | 50% | 100%
| 1.2 | Establish a Process | Medium | Medium | NA | NA | High | High | NA | NA | High | NA | 25% | 100%
| 1.3 | Develop Scenarios | Medium | Low | Medium | NA | NA | NA | NA | NA | Medium | NA | 0% | 100%
2 | Requirements Analysis
| 2.1 | Define Information Content and Context | High | Medium | NA | Medium | High | NA | NA | NA | Medium | High | 0% | 100%
| 2.2 | Build Domain Model | High | NA | NA | Low | Low | NA | NA | NA | NA | High | 0% | 100%
3 | Mapping and Modeling
| 3.1 | Mapping | High | Low | NA | Low | Low | NA | NA | NA | NA | Low | 0% | 75%
| 3.2 | Define Terms with Exchange Partner | Medium | NA | NA | Low | High | NA | NA | NA | NA | Low | 25% | 50%
4 | Building and Validating
| 4.1 | Identify NIEM Reference Schemas | NA | NA | NA | Medium | NA | NA | NA | NA | NA | NA | 25% | 50%
| 4.2.1 | Create NIEM Subset Schema | Low | NA | NA | NA | NA | NA | NA | NA | NA | NA | 25% | 50%
| 4.2.2 | Create Extension Schema or Entire Schema (for Custom XML) | High | NA | NA | High | NA | NA | NA | NA | NA | NA | 25% | 50%
| 4.2.3 | Create Exchange Schema | Medium | NA | NA | Medium | NA | NA | NA | NA | NA | NA | 50% | 50%
| 4.3 | Build Constraint Schema | Medium | NA | NA | Medium | NA | NA | NA | NA | NA | Low | 50% | 50%
| 4.4 | Validate Schema | Medium | NA | NA | Medium | NA | NA | NA | Low | NA | NA | 50% | 50%
5 | Assemble and Document
| 5.1 | Develop NIEM Meta-Data Schema | Medium | NA | NA | Medium | NA | NA | NA | NA | Low | NA | 25% | 50%
| 5.2 | Assemble Required IEPD Artifacts | Medium | NA | NA | NA | Medium | NA | NA | NA | Low | NA | 25% | 50%
6 | Publish IEPD
| 6.1 | Publish IEPD to Repository | Medium | NA | NA | NA | Low | NA | NA | NA | Low | NA | 25% | 50%
7 | Data Exchange Design Implementation
| 7.1 | Design Instance Creation Rules (Sender) | Low | Low | Low | Medium | Low | NA | NA | NA | NA | Low | 0% | 50%
| 7.2 | Design Instance Processing Rules (Receiver) | Low | Low | Low | Medium | Low | NA | NA | NA | NA | NA | 0% | 50%
| 7.3 | Design Instance middleware routing rules based on data exchange | Low | Low | Low | Medium | Low | NA | NA | NA | NA | NA | 25% | 50%
| 7.4 | Document Business Use Cases for data exchange | Medium | NA | NA | NA | NA | NA | NA | NA | NA | Low | 0% | 50%
| 7.5 | Document Business Test Cases for data exchange | Low | NA | NA | NA | Low | NA | NA | High | NA | NA | 0% | 50%
| 7.6 | MOU's for Data Exchange and Network Services | NA | NA | Low | NA | Medium | Low | NA | NA | Medium | NA | 50% | 50%
8 | Data Exchange Development and Implementation
| 8.1 | Develop Instance and Implement Creation Rules | Low | Low | Low | High | Low | NA | NA | NA | NA | NA | 25% | 100%
| 8.2 | Develop Instance receiver and related system processing rules | Low | Low | Low | High | Low | NA | NA | NA | NA | NA | 25% | 100%
| 8.3 | Develop middleware data exchange business process and routing rules based on the business case | Low | Low | Low | High | NA | NA | NA | NA | NA | NA | 25% | 100%
9 | Data Exchange Testing
| 9.1 | Unit Test - sending Instance and business triggering events | Low | NA | NA | Low | Low | NA | NA | Medium | NA | NA | 75% | 100%
| 9.2 | Unit Test - receiving Instance and related display in receiving system | Low | NA | NA | Low | Low | NA | NA | Medium | NA | NA | 75% | 100%
| 9.3 | Unit Test - middleware for data exchange instance routing rules based on the business case | Low | NA | NA | Low | Low | NA | NA | Medium | NA | NA | 75% | 100%
| 9.4 | Integration Test - send Instance based on testing scenarios | Low | NA | NA | Low | Low | NA | NA | Medium | NA | NA | 50% | 100%
| 9.5 | Integration Test - receiving Instance based on testing scenarios | Low | NA | NA | Low | Low | NA | NA | Medium | NA | NA | 50% | 100%
| 9.6 | Integration Test - routing and business transformation rules for the instance | Low | NA | NA | Low | Low | NA | NA | Medium | NA | Low | 50% | 100%
10 | Data Exchange Deployment
| 10.1 | Deploy Instance Sending Software | NA | Medium | NA | NA | NA | NA | NA | NA | NA | NA | 0% | 100%
| 10.2 | Deploy Instance Receiving Software | NA | Medium | NA | NA | NA | NA | NA | NA | NA | NA | 0% | 100%
| 10.3 | Deploy Instance routing and business rule logic | NA | Medium | NA | NA | NA | NA | NA | NA | NA | NA | 0% | 100%

## 5.0 Summary Analysis
NIEM Cost Model v. 2.0 (Medium Participation)
Summary Analysis
Back to Overview
Four-Year NIEM Cost Summary
|  | Base Year | Year 1 | Year 2 | Year 3
| Number of Exchanges | 2 | 3 | 4 | 5
Revenue
| Funded Amount | 0 | 0 | 0 | 0
| Adjustment from Previous Year | N/A | -851425.32 | -1367566.68 | -2054833.58
| Total Revenue | 0 | -851425.32 | -1367566.68 | -2054833.58
Expenses
Scenario Planning
| Establish a Vision | 35122.2 | 35122.2 | 46829.6 | 58537
| Establish a Process | 68817 | 41290.2 | 55053.6 | 68817
| Develop Scenarios | 27725.2 | 0 | 0 | 0
| Scenario Planning Total | 131664.4 | 76412.4 | 101883.2 | 127354
Requirements Analysis
| Define Information Content and Context | 56365.2 | 0 | 0 | 0
| Build Domain Model | 28104.8 | 0 | 0 | 0
| Requirements Analysis Total | 84470 | 0 | 0 | 0
Mapping & Modeling
| Mapping | 24366 | 0 | 0 | 0
| Define Terms with Exchange Partner | 31496 | 18897.6 | 25196.8 | 31496
| Mapping & Modeling Total | 55862 | 18897.6 | 25196.8 | 31496
Building & Validating
| Identify NIEM Reference Schemas | 9201 | 5520.6 | 7360.8 | 9201
| Create NIEM Subset Schema | 3528 | 2116.8 | 2822.4 | 3528
| Create Extension Schema | 24385.5 | 14631.3 | 19508.4 | 24385.5
| Create Exchange Schema | 19508.4 | 19508.4 | 26011.2 | 32514
| Build Constraint Schema | 25508.4 | 25508.4 | 34011.2 | 42514
| Validate Schema | 23041.92 | 23041.92 | 30722.56 | 38403.2
| Building & Validating Total | 105173.22 | 90327.42 | 120436.56 | 150545.7
Assemble & Document
| Develop NIEM Meta-Data Schema | 21346.5 | 12807.9 | 17077.2 | 21346.5
| Assemble Required IEPD Artifacts | 22038.5 | 13223.1 | 17630.8 | 22038.5
| Assemble & Document Total | 43385 | 26031 | 34708 | 43385
Publish IEPD
| Publish IEPD to Repository | 17092 | 10255.2 | 13673.6 | 17092
| Total Publish IEPD | 17092 | 10255.2 | 13673.6 | 17092
Data Exchange Design Implementation
| Design NIEM Instance Creation Rules (Sender) | 27239.6 | 0 | 0 | 0
| Design NIEM Instance Processing Rules (Receiver) | 23239.6 | 0 | 0 | 0
| Design NIEM Instance middleware routing rules based on data exchange | 29049.5 | 17429.7 | 23239.6 | 29049.5
| Document Business Use Cases for data exchange | 9644.8 | 0 | 0 | 0
| Document Business Test Cases for data exchange | 13846.64 | 0 | 0 | 0
| MOU's for Data Exchange and Network Services | 39743.4 | 39743.4 | 52991.2 | 66239
| Data Exchange Design Implementation Total | 142763.54 | 57173.1 | 76230.8 | 95288.5
Data Exchange Development and Implementation
| Develop NIEM Instance and Implement Creation Rules | 33650 | 20190 | 26920 | 33650
| Develop NIEM Instance receiver and related system processing rules | 33650 | 20190 | 26920 | 33650
| Develop middleware data exchange business process and routing rules based on the business case | 28703.5 | 17222.1 | 22962.8 | 28703.5
| Data Exchange Development and Implementation Total | 96003.5 | 57602.1 | 76802.8 | 96003.5
Data Exchange Testing
| Unit Test - sending NIEM Instance and business triggering events | 26549.88 | 34135.56 | 45514.08 | 56892.6
| Unit Test - receiving NIEM Instance and related display in receiving system | 26549.88 | 34135.56 | 45514.08 | 56892.6
| Unit Test - middleware for NIEM data exchange instance routing rules based on the business case | 26549.88 | 34135.56 | 45514.08 | 56892.6
| Integration Test - send NIEM Instance based on testing scenarios | 22757.04 | 22757.04 | 30342.72 | 37928.4
| Integration Test - receiving NIEM Instance based on testing scenarios | 22757.04 | 22757.04 | 30342.72 | 37928.4
| Integration Test - routing and business transformation rules for the NIEM instance | 28757.04 | 28757.04 | 38342.72 | 47928.4
| Data Exchange Testing Total | 153920.76 | 176677.8 | 235570.4 | 294463
Data Exchange Deployment
| Deploy NIEM Instance Sending Software | 8522.4 | 0 | 0 | 0
| Deploy NIEM Instance Receiving Software | 8522.4 | 0 | 0 | 0
| Deploy NIEM Instance routing and business rule logic | 8522.4 | 0 | 0 | 0
| Data Exchange Deployment Total | 25567.2 | 0 | 0 | 0
Additional Costs
| Hardware | 0 | 0 | 0 | 0
| Software | 0 | 0 | 0 | 0
| Training (Onetime Cost) | 6700 | 5000 | 5000 | 5000
| Additional Costs Total | 6700 | 5000 | 5000 | 5000
Discount Factors
| There is an Existing IEPD | 0 | 0 | 0 | 0
| Adjustment Because All Elements Already Exist in NIEM | 0 | -2235.26 | -2235.26 | -2235.26
| Adjustment of cost benefit from becoming a part of the NIEM Community | -11176.3 | 0 | 0 | 0
| Discount Factors Total | -11176.3 | -2235.26 | -2235.26 | -2235.26
| Total Expenses | 851425.32 | 516141.36 | 687266.9 | 858392.44
| Balance | -851425.32 | -1367566.68 | -2054833.58 | -2913226.02
Average Costs
| Average Cost Savings per Year | 0 | 760996.62 | 1015583.74 | 1270170.86
| Average Cost per Exchange | 425712.66 | 172047.12 | 171816.725 | 171678.488
| Average Cost Savings per Exchange | 0 | 253665.54 | 253895.935 | 254034.172
Quantitative Benefits Cash Flow
| Benefit Category/Benefit Identified | Year 0 | Year 1 | Year 2 | Year 3
| Data Components & Tools Reusability | 650 | 780 | 1092 | 1747.2
| A | 250 | 300 | 420 | 672
| B | 400 | 480 | 672 | 1075.2
| Design & Development | 550 | 660 | 924 | 1478.4
| C | 100 | 120 | 168 | 268.8
| D | 450 | 540 | 756 | 1209.6
| Information Sharing Quality | 2000 | 2400 | 3360 | 5376
| E | 1000 | 1200 | 1680 | 2688
| F | 1000 | 1200 | 1680 | 2688
| Scalability | 3500 | 4200 | 5880 | 9408
| G | 2000 | 2400 | 3360 | 5376
| H | 1500 | 1800 | 2520 | 4032
| Standardization | 5000 | 6000 | 8400 | 13440
| I | 3000 | 3600 | 5040 | 8064
| J | 2000 | 2400 | 3360 | 5376
| Interoperability | 1450 | 1740 | 2436 | 3897.6
| K | 500 | 600 | 840 | 1344
| L | 950 | 1140 | 1596 | 2553.6
| Total Quantitative Benefits | 13150 | 15780 | 22092 | 35347.2
Financial Calculations
| Net Present Value (NPV) | -838275.32 | -495407.2871 | -652068.3266 | -798839.6012
| Internal Rate of Return (IRR) | -2893066.4906 | -2023969.303 | -1500753.8239 | -823045.24
Return on Investment (ROI)
Payback
Note on C104: Kim, Song Ki: Calculations based on Scorecard and other Variables.

## 5.1 Base YR
NIEM Cost Model v. 2.0 (Medium Participation)
Base Year Analysis
Back to Overview
NIEM Exchange
|  |  |  | Initial Exchange | Additional Exchange (Same Data) | Additional Exchange (New Data) | Total Cost to build 1 NIEM exchange and reuse 1 NIEM exchanges
Recurring Costs
| 1 | Scenario Planning
|  | 1.1 | Establish a Vision | 23414.8 | 11707.4 | 0 | 35122.2
|  | 1.2 | Establish a Process | 55053.6 | 13763.4 | 0 | 68817
|  | 1.3 | Develop Scenarios | 27725.2 | 0 | 0 | 27725.2
|  |  | Total | 106193.6 | 25470.8 | 0 | 131664.4
| 2 | Requirements Analysis
|  | 2.1 | Define Information Content and Context | 56365.2 | 0 | 0 | 56365.2
|  | 2.2 | Build Domain Model | 28104.8 | 0 | 0 | 28104.8
|  |  | Total | 84470 | 0 | 0 | 84470
| 3 | Mapping and Modeling
|  | 3.1 | Mapping | 24366 | 0 | 0 | 24366
|  | 3.2 | Define Terms with Exchange Partner | 25196.8 | 6299.2 | 0 | 31496
|  |  | Total | 49562.8 | 6299.2 | 0 | 55862
| 4 | Building and Validating
|  | 4.1 | Identify Reference Schemas | 7360.8 | 1840.2 | 0 | 9201
|  | 4.2.1 | Create Subset Schema | 2822.4 | 705.6 | 0 | 3528
|  | 4.2.2 | Create Extension Schema | 19508.4 | 4877.1 | 0 | 24385.5
|  | 4.2.3 | Create Exchange Schema | 13005.6 | 6502.8 | 0 | 19508.4
|  | 4.3 | Build Constraint Schema | 17005.6 | 8502.8 | 0 | 25508.4
|  | 4.4 | Validate Schema | 15361.28 | 7680.64 | 0 | 23041.92
|  |  | Total | 75064.08 | 30109.14 | 0 | 105173.22
| 5 | Assemble and Document
|  | 5.1 | Develop Meta-Data Schema | 17077.2 | 4269.3 | 0 | 21346.5
|  | 5.2 | Assemble Required IEPD Artifacts | 17630.8 | 4407.7 | 0 | 22038.5
|  |  | Total | 34708 | 8677 | 0 | 43385
| 6 | Publish IEPD
|  | 6.1 | Publish IEPD to Repository | 13673.6 | 3418.4 | 0 | 17092
|  |  | Total | 13673.6 | 3418.4 | 0 | 17092
| 7 | Data Exchange Design Implementation
|  | 7.1 | Design Instance Creation Rules (Sender) | 27239.6 | 0 | 0 | 27239.6
|  | 7.2 | Design Instance Processing Rules (Receiver) | 23239.6 | 0 | 0 | 23239.6
|  | 7.3 | Design Instance middleware routing rules based on data exchange | 23239.6 | 5809.9 | 0 | 29049.5
|  | 7.4 | Document Business Use Cases for data exchange | 9644.8 | 0 | 0 | 9644.8
|  | 7.5 | Document Business Test Cases for data exchange | 13846.64 | 0 | 0 | 13846.64
|  | 7.6 | MOU's for Data Exchange and Network Services | 26495.6 | 13247.8 | 0 | 39743.4
|  |  | Total | 123705.84 | 19057.7 | 0 | 142763.54
| 8 | Data Exchange Development and Implementation
|  | 8.1 | Develop Instance and Implement Creation Rules | 26920 | 6730 | 0 | 33650
|  | 8.2 | Develop Instance receiver and related system processing rules | 26920 | 6730 | 0 | 33650
|  | 8.3 | Develop middleware data exchange business process and routing rules based on the business case | 22962.8 | 5740.7 | 0 | 28703.5
|  |  | Total | 76802.8 | 19200.7 | 0 | 96003.5
| 9 | Data Exchange Testing
|  | 9.1 | Unit Test - sending Instance and business triggering events | 15171.36 | 11378.52 | 0 | 26549.88
|  | 9.2 | Unit Test - receiving Instance and related display in receiving system | 15171.36 | 11378.52 | 0 | 26549.88
|  | 9.3 | Unit Test - middleware for data exchange instance routing rules based on the business case | 15171.36 | 11378.52 | 0 | 26549.88
|  | 9.4 | Integration Test - send Instance based on testing scenarios | 15171.36 | 7585.68 | 0 | 22757.04
|  | 9.5 | Integration Test - receiving Instance based on testing scenarios | 15171.36 | 7585.68 | 0 | 22757.04
|  | 9.6 | Integration Test - routing and business transformation rules for the instance | 19171.36 | 9585.68 | 0 | 28757.04
|  |  | Total | 95028.16 | 58892.6 | 0 | 153920.76
| 10 | Data Exchange Deployment
|  | 10.1 | Deploy Instance Sending Software | 8522.4 | 0 | 0 | 8522.4
|  | 10.2 | Deploy Instance Receiving Software | 8522.4 | 0 | 0 | 8522.4
|  | 10.3 | Deploy Instance routing and business rule logic | 8522.4 | 0 | 0 | 8522.4
|  |  | Total | 25567.2 | 0 | 0 | 25567.2
| Total Recurring Costs |  |  | 684776.08 | 171125.54 | 0 | 855901.62
Other Costs
|  |  | Hardware Cost | 0 | 0 | 0 | 0
|  |  | Software Cost | 0 | 0 | 0 | 0
|  |  | Training | 6700 | 0 | 0 | 6700
|  |  | Total | 6700 | 0 | 0 | 6700
Discount Factors
|  |  | There is not and existing IEPD | 0 | 0 | 0 | 0
|  |  | Adjustment because Some (<50%) Elements Already Exist in NIEM | -8941.04 | -2235.26 | 0 | -11176.3
|  |  | Adjustment of cost benefit from becoming a part of the NIEM Community | 0 | 0 | 0 | 0
|  |  | Total | -8941.04 | -2235.26 | 0 | -11176.3
| Total Cost |  |  | 682535.04 | 168890.28 | 0 | 851425.32
Note on D85: If there is an existing IEPD, the model will take out the costs associated with tasks 2.2, 3.1, 4.1, 4.2.1 and 4.2.3
Note on D87: This is based on the Model Overlap Escalation factors (see Cost Variables sheet) and the costs associated with Define Terms with Exchange Partners (3.2) and Create Extension Schema Costs (4.2.2).

## 5.2 YR1
NIEM Cost Model v. 2.0 (Medium Participation)
Year 1 Analysis
Back to Overview
NIEM Exchange
|  |  |  | Initial Exchange from Previous Year | Additional Exchange (Same Data) | Additional Exchange (New Data) | Total Cost to build 0 NIEM exchanges and reuse 3 NIEM exchanges
Recurring Costs
| 1 | Scenario Planning
|  | 1.1 | Establish a Vision | 23414.8 | 11707.4 | 0 | 35122.2
|  | 1.2 | Establish a Process | 55053.6 | 13763.4 | 0 | 41290.2
|  | 1.3 | Develop Scenarios | 27725.2 | 0 | 0 | 0
|  |  | Total | 106193.6 | 25470.8 | 0 | 76412.4
| 2 | Requirements Analysis
|  | 2.1 | Define Information Content and Context | 56365.2 | 0 | 0 | 0
|  | 2.2 | Build Domain Model | 28104.8 | 0 | 0 | 0
|  |  | Total | 84470 | 0 | 0 | 0
| 3 | Mapping and Modeling
|  | 3.1 | Mapping | 24366 | 0 | 0 | 0
|  | 3.2 | Define Terms with Exchange Partner | 25196.8 | 6299.2 | 0 | 18897.6
|  |  | Total | 49562.8 | 6299.2 | 0 | 18897.6
| 4 | Building and Validating
|  | 4.1 | Identify NIEM Reference Schemas | 7360.8 | 1840.2 | 0 | 5520.6
|  | 4.2.1 | Create NIEM Subset Schema | 2822.4 | 705.6 | 0 | 2116.8
|  | 4.2.2 | Create Extension Schema | 19508.4 | 4877.1 | 0 | 14631.3
|  | 4.2.3 | Create Exchange Schema | 13005.6 | 6502.8 | 0 | 19508.4
|  | 4.3 | Build Constraint Schema | 17005.6 | 8502.8 | 0 | 25508.4
|  | 4.4 | Validate Schema | 15361.28 | 7680.64 | 0 | 23041.92
|  |  | Total | 75064.08 | 30109.14 | 0 | 90327.42
| 5 | Assemble and Document
|  | 5.1 | Develop NIEM Meta-Data Schema | 17077.2 | 4269.3 | 0 | 12807.9
|  | 5.2 | Assemble Required IEPD Artifacts | 17630.8 | 4407.7 | 0 | 13223.1
|  |  | Total | 34708 | 8677 | 0 | 26031
| 6 | Publish IEPD
|  | 6.1 | Publish IEPD to Repository | 13673.6 | 3418.4 | 0 | 10255.2
|  |  | Total | 13673.6 | 3418.4 | 0 | 10255.2
| 7 | Data Exchange Design Implementation
|  | 7.1 | Design Instance Creation Rules (Sender) | 27239.6 | 0 | 0 | 0
|  | 7.2 | Design Instance Processing Rules (Receiver) | 23239.6 | 0 | 0 | 0
|  | 7.3 | Design Instance middleware routing rules based on data exchange | 23239.6 | 5809.9 | 0 | 17429.7
|  | 7.4 | Document Business Use Cases for data exchange | 9644.8 | 0 | 0 | 0
|  | 7.5 | Document Business Test Cases for data exchange | 13846.64 | 0 | 0 | 0
|  | 7.6 | MOU's for Data Exchange and Network Services | 26495.6 | 13247.8 | 0 | 39743.4
|  |  | Total | 123705.84 | 19057.7 | 0 | 57173.1
| 8 | Data Exchange Development and Implementation
|  | 8.1 | Develop Instance and Implement Creation Rules | 26920 | 6730 | 0 | 20190
|  | 8.2 | Develop Instance receiver and related system processing rules | 26920 | 6730 | 0 | 20190
|  | 8.3 | Develop middleware data exchange business process and routing rules based on the business case | 22962.8 | 5740.7 | 0 | 17222.1
|  |  | Total | 76802.8 | 19200.7 | 0 | 57602.1
| 9 | Data Exchange Testing
|  | 9.1 | Unit Test - sending Instance and business triggering events | 15171.36 | 11378.52 | 0 | 34135.56
|  | 9.2 | Unit Test - receiving Instance and related display in receiving system | 15171.36 | 11378.52 | 0 | 34135.56
|  | 9.3 | Unit Test - middleware for data exchange instance routing rules based on the business case | 15171.36 | 11378.52 | 0 | 34135.56
|  | 9.4 | Integration Test - send Instance based on testing scenarios | 15171.36 | 7585.68 | 0 | 22757.04
|  | 9.5 | Integration Test - receiving Instance based on testing scenarios | 15171.36 | 7585.68 | 0 | 22757.04
|  | 9.6 | Integration Test - routing and business transformation rules for the instance | 19171.36 | 9585.68 | 0 | 28757.04
|  |  | Total | 95028.16 | 58892.6 | 0 | 176677.8
| 10 | Data Exchange Deployment
|  | 10.1 | Deploy Instance Sending Software | 8522.4 | 0 | 0 | 0
|  | 10.2 | Deploy Instance Receiving Software | 8522.4 | 0 | 0 | 0
|  | 10.3 | Deploy Instance routing and business rule logic | 8522.4 | 0 | 0 | 0
|  |  | Total | 25567.2 | 0 | 0 | 0
| Total Recurring Costs |  |  | 684776.08 | 171125.54 | 0 | 513376.62
Other Costs
|  |  | Hardware Cost | 0 | 0 | 0 | 0
|  |  | Software Cost | 0 | 0 | 0 | 0
|  |  | Training | 6700 | 5000 | 0 | 5000
|  |  | Total | 6700 | 5000 | 0 | 5000
Discount Factors
|  |  | There is not and existing IEPD | 0 | 0 | 0 | 0
|  |  | Adjustment because Some (<50%) Elements Already Exist in NIEM | -8941.04 | -2235.26 | 0 | -2235.26
|  |  | Adjustment of cost benefit from becoming a part of the NIEM Community | 0 | 0 | 0 | 0
|  |  | Total | -8941.04 | -2235.26 | 0 | -2235.26
| Total Cost |  |  | 682535.04 | 173890.28 | 0 | 516141.36
Note on D85: If there is an existing IEPD, the model will take out the costs associated with tasks 2.2, 3.1, 4.1, 4.2.1 and 4.2.3
Note on D87: This is based on the Model Overlap Escalation factors (see Cost Variables sheet) and the costs associated with Define Terms with Exchange Partners (3.2) and Create Extension Schema Costs (4.2.2).

## 5.3 YR2
NIEM Cost Model v. 2.0 (Medium Participation)
Year 2 Analysis
Back to Overview
NIEM Exchange
|  |  |  | Initial Exchange from Previous Year | Additional Exchange (Same Data) | Additional Exchange (New Data) | Total Cost to build 0 NIEM exchanges and reuse 4 NIEM exchanges
Recurring Costs
| 1 | Scenario Planning
|  | 1.1 | Establish a Vision | 23414.8 | 11707.4 | 0 | 46829.6
|  | 1.2 | Establish a Process | 55053.6 | 13763.4 | 0 | 55053.6
|  | 1.3 | Develop Scenarios | 27725.2 | 0 | 0 | 0
|  |  | Total | 106193.6 | 25470.8 | 0 | 101883.2
| 2 | Requirements Analysis
|  | 2.1 | Define Information Content and Context | 56365.2 | 0 | 0 | 0
|  | 2.2 | Build Domain Model | 28104.8 | 0 | 0 | 0
|  |  | Total | 84470 | 0 | 0 | 0
| 3 | Mapping and Modeling
|  | 3.1 | Mapping | 24366 | 0 | 0 | 0
|  | 3.2 | Define Terms with Exchange Partner | 25196.8 | 6299.2 | 0 | 25196.8
|  |  | Total | 49562.8 | 6299.2 | 0 | 25196.8
| 4 | Building and Validating
|  | 4.1 | Identify NIEM Reference Schemas | 7360.8 | 1840.2 | 0 | 7360.8
|  | 4.2.1 | Create NIEM Subset Schema | 2822.4 | 705.6 | 0 | 2822.4
|  | 4.2.2 | Create Extension Schema | 19508.4 | 4877.1 | 0 | 19508.4
|  | 4.2.3 | Create Exchange Schema | 13005.6 | 6502.8 | 0 | 26011.2
|  | 4.3 | Build Constraint Schema | 17005.6 | 8502.8 | 0 | 34011.2
|  | 4.4 | Validate Schema | 15361.28 | 7680.64 | 0 | 30722.56
|  |  | Total | 75064.08 | 30109.14 | 0 | 120436.56
| 5 | Assemble and Document
|  | 5.1 | Develop NIEM Meta-Data Schema | 17077.2 | 4269.3 | 0 | 17077.2
|  | 5.2 | Assemble Required IEPD Artifacts | 17630.8 | 4407.7 | 0 | 17630.8
|  |  | Total | 34708 | 8677 | 0 | 34708
| 6 | Publish IEPD
|  | 6.1 | Publish IEPD to Repository | 13673.6 | 3418.4 | 0 | 13673.6
|  |  | Total | 13673.6 | 3418.4 | 0 | 13673.6
| 7 | Data Exchange Design Implementation
|  | 7.1 | Design Instance Creation Rules (Sender) | 27239.6 | 0 | 0 | 0
|  | 7.2 | Design Instance Processing Rules (Receiver) | 23239.6 | 0 | 0 | 0
|  | 7.3 | Design Instance middleware routing rules based on data exchange | 23239.6 | 5809.9 | 0 | 23239.6
|  | 7.4 | Document Business Use Cases for data exchange | 9644.8 | 0 | 0 | 0
|  | 7.5 | Document Business Test Cases for data exchange | 13846.64 | 0 | 0 | 0
|  | 7.6 | MOU's for Data Exchange and Network Services | 26495.6 | 13247.8 | 0 | 52991.2
|  |  | Total | 123705.84 | 19057.7 | 0 | 76230.8
| 8 | Data Exchange Development and Implementation
|  | 8.1 | Develop Instance and Implement Creation Rules | 26920 | 6730 | 0 | 26920
|  | 8.2 | Develop Instance receiver and related system processing rules | 26920 | 6730 | 0 | 26920
|  | 8.3 | Develop middleware data exchange business process and routing rules based on the business case | 22962.8 | 5740.7 | 0 | 22962.8
|  |  | Total | 76802.8 | 19200.7 | 0 | 76802.8
| 9 | Data Exchange Testing
|  | 9.1 | Unit Test - sending Instance and business triggering events | 15171.36 | 11378.52 | 0 | 45514.08
|  | 9.2 | Unit Test - receiving Instance and related display in receiving system | 15171.36 | 11378.52 | 0 | 45514.08
|  | 9.3 | Unit Test - middleware for data exchange instance routing rules based on the business case | 15171.36 | 11378.52 | 0 | 45514.08
|  | 9.4 | Integration Test - send Instance based on testing scenarios | 15171.36 | 7585.68 | 0 | 30342.72
|  | 9.5 | Integration Test - receiving Instance based on testing scenarios | 15171.36 | 7585.68 | 0 | 30342.72
|  | 9.6 | Integration Test - routing and business transformation rules for the instance | 19171.36 | 9585.68 | 0 | 38342.72
|  |  | Total | 95028.16 | 58892.6 | 0 | 235570.4
| 10 | Data Exchange Deployment
|  | 10.1 | Deploy Instance Sending Software | 8522.4 | 0 | 0 | 0
|  | 10.2 | Deploy Instance Receiving Software | 8522.4 | 0 | 0 | 0
|  | 10.3 | Deploy Instance routing and business rule logic | 8522.4 | 0 | 0 | 0
|  |  | Total | 25567.2 | 0 | 0 | 0
| Total Recurring Costs |  |  | 684776.08 | 171125.54 | 0 | 684502.16
Other Costs
|  |  | Hardware Cost | 0 | 0 | 0 | 0
|  |  | Software Cost | 0 | 0 | 0 | 0
|  |  | Training | 6700 | 5000 | 0 | 5000
|  |  | Total | 6700 | 5000 | 0 | 5000
Discount Factors
|  |  | There is not and existing IEPD | 0 | 0 | 0 | 0
|  |  | Adjustment because Some (<50%) Elements Already Exist in NIEM | -8941.04 | -2235.26 | 0 | -2235.26
|  |  | Adjustment of cost benefit from becoming a part of the NIEM Community | 0 | 0 | 0 | 0
|  |  | Total | -8941.04 | -2235.26 | 0 | -2235.26
| Total Cost |  |  | 682535.04 | 173890.28 | 0 | 687266.9
Note on D85: If there is an existing IEPD, the model will take out the costs associated with tasks 2.2, 3.1, 4.1, 4.2.1 and 4.2.3
Note on D86: This is based on the Model Overlap Escalation factors (see Cost Variables sheet) and the costs associated with Define Terms with Exchange Partners (3.2) and Create Extension Schema Costs (4.2.2).
Note on D87: This is based on the Model Overlap Escalation factors (see Cost Variables sheet) and the costs associated with Define Terms with Exchange Partners (3.2) and Create Extension Schema Costs (4.2.2).

## 5.4 YR3
NIEM Cost Model v. 2.0 (Medium Participation)
Year 3 Analysis
Back to Overview
NIEM Exchange
|  |  |  | Initial Exchange from Previous Year | Additional Exchange (Same Data) | Additional Exchange (New Data) | Total Cost to build 0 NIEM exchanges and reuse 5 NIEM exchanges
Recurring Costs
| 1 | Scenario Planning
|  | 1.1 | Establish a Vision | 23414.8 | 11707.4 | 0 | 58537
|  | 1.2 | Establish a Process | 55053.6 | 13763.4 | 0 | 68817
|  | 1.3 | Develop Scenarios | 27725.2 | 0 | 0 | 0
|  |  | Total | 106193.6 | 25470.8 | 0 | 127354
| 2 | Requirements Analysis
|  | 2.1 | Define Information Content and Context | 56365.2 | 0 | 0 | 0
|  | 2.2 | Build Domain Model | 28104.8 | 0 | 0 | 0
|  |  | Total | 84470 | 0 | 0 | 0
| 3 | Mapping and Modeling
|  | 3.1 | Mapping | 24366 | 0 | 0 | 0
|  | 3.2 | Define Terms with Exchange Partner | 25196.8 | 6299.2 | 0 | 31496
|  |  | Total | 49562.8 | 6299.2 | 0 | 31496
| 4 | Building and Validating
|  | 4.1 | Identify NIEM Reference Schemas | 7360.8 | 1840.2 | 0 | 9201
|  | 4.2.1 | Create NIEM Subset Schema | 2822.4 | 705.6 | 0 | 3528
|  | 4.2.2 | Create Extension Schema | 19508.4 | 4877.1 | 0 | 24385.5
|  | 4.2.3 | Create Exchange Schema | 13005.6 | 6502.8 | 0 | 32514
|  | 4.3 | Build Constraint Schema | 17005.6 | 8502.8 | 0 | 42514
|  | 4.4 | Validate Schema | 15361.28 | 7680.64 | 0 | 38403.2
|  |  | Total | 75064.08 | 30109.14 | 0 | 150545.7
| 5 | Assemble and Document
|  | 5.1 | Develop NIEM Meta-Data Schema | 17077.2 | 4269.3 | 0 | 21346.5
|  | 5.2 | Assemble Required IEPD Artifacts | 17630.8 | 4407.7 | 0 | 22038.5
|  |  | Total | 34708 | 8677 | 0 | 43385
| 6 | Publish IEPD
|  | 6.1 | Publish IEPD to Repository | 13673.6 | 3418.4 | 0 | 17092
|  |  | Total | 13673.6 | 3418.4 | 0 | 17092
| 7 | Data Exchange Design Implementation
|  | 7.1 | Design Instance Creation Rules (Sender) | 27239.6 | 0 | 0 | 0
|  | 7.2 | Design Instance Processing Rules (Receiver) | 23239.6 | 0 | 0 | 0
|  | 7.3 | Design Instance middleware routing rules based on data exchange | 23239.6 | 5809.9 | 0 | 29049.5
|  | 7.4 | Document Business Use Cases for data exchange | 9644.8 | 0 | 0 | 0
|  | 7.5 | Document Business Test Cases for data exchange | 13846.64 | 0 | 0 | 0
|  | 7.6 | MOU's for Data Exchange and Network Services | 26495.6 | 13247.8 | 0 | 66239
|  |  | Total | 123705.84 | 19057.7 | 0 | 95288.5
| 8 | Data Exchange Development and Implementation
|  | 8.1 | Develop Instance and Implement Creation Rules | 26920 | 6730 | 0 | 33650
|  | 8.2 | Develop Instance receiver and related system processing rules | 26920 | 6730 | 0 | 33650
|  | 8.3 | Develop middleware data exchange business process and routing rules based on the business case | 22962.8 | 5740.7 | 0 | 28703.5
|  |  | Total | 76802.8 | 19200.7 | 0 | 96003.5
| 9 | Data Exchange Testing
|  | 9.1 | Unit Test - sending Instance and business triggering events | 15171.36 | 11378.52 | 0 | 56892.6
|  | 9.2 | Unit Test - receiving Instance and related display in receiving system | 15171.36 | 11378.52 | 0 | 56892.6
|  | 9.3 | Unit Test - middleware for data exchange instance routing rules based on the business case | 15171.36 | 11378.52 | 0 | 56892.6
|  | 9.4 | Integration Test - send Instance based on testing scenarios | 15171.36 | 7585.68 | 0 | 37928.4
|  | 9.5 | Integration Test - receiving Instance based on testing scenarios | 15171.36 | 7585.68 | 0 | 37928.4
|  | 9.6 | Integration Test - routing and business transformation rules for the instance | 19171.36 | 9585.68 | 0 | 47928.4
|  |  | Total | 95028.16 | 58892.6 | 0 | 294463
| 10 | Data Exchange Deployment
|  | 10.1 | Deploy Instance Sending Software | 8522.4 | 0 | 0 | 0
|  | 10.2 | Deploy Instance Receiving Software | 8522.4 | 0 | 0 | 0
|  | 10.3 | Deploy Instance routing and business rule logic | 8522.4 | 0 | 0 | 0
|  |  | Total | 25567.2 | 0 | 0 | 0
| Total Recurring Costs |  |  | 684776.08 | 171125.54 | 0 | 855627.7
Other Costs
|  |  | Hardware Cost | 0 | 0 | 0 | 0
|  |  | Software Cost | 0 | 0 | 0 | 0
|  |  | Training | 6700 | 5000 | 0 | 5000
|  |  | Total | 6700 | 5000 | 0 | 5000
Discount Factors
|  |  | There is not and existing IEPD | 0 | 0 | 0 | 0
|  |  | Adjustment because Some (<50%) Elements Already Exist in NIEM | -8941.04 | -2235.26 | 0 | -2235.26
|  |  | Adjustment of cost benefit from becoming a part of the NIEM Community | 0 | 0 | 0 | 0
|  |  | Total | -8941.04 | -2235.26 | 0 | -2235.26
| Total Cost |  |  | 682535.04 | 173890.28 | 0 | 858392.44
Note on D85: If there is an existing IEPD, the model will take out the costs associated with tasks 2.2, 3.1, 4.1, 4.2.1 and 4.2.3
Note on D87: This is based on the Model Overlap Escalation factors (see Cost Variables sheet) and the costs associated with Define Terms with Exchange Partners (3.2) and Create Extension Schema Costs (4.2.2).

## 6.0 Metrics (hidden)
6.0 Metrics
Overview | Back to Overview
Dashboard | Back to Dashboard
Performance Metrics
| Metric |  | Current | Goal | Actual (Time Elapsed after NIEM Implementation)
[5 empty] | 6 Months | 12 Months | 18 Months | 24 Months | 30 Months | 36 Months
| Number of exchange partners |  | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0
| User satisfaction with information sharing process (in % users satisfied) |  | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0
| Time to complete an exchange (in seconds) |  | 30 | 25 | 0 | 0 | 0 | 0 | 0 | 0
| Number of manual vs automated steps involved in the information sharing process | Manual | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Automated | 2 | 4 | 0 | 0 | 0 | 0 | 0 | 0
| Benefits Category | Description of Benefits |  |  | Benefits Quantified
| 1.0 Data Components & Tools Reusability | Provides greater efficiency, effectiveness, and return on investment (ROI) in operations and decision making by providing users with a set of reusable data components, as well as the tools needed for discovering and developing common and universal data for effective information exchange. |  |  | Data Components Tools
| 2.0 Design & Development | Reduces the design and development time needed to build and implement robust, agile information sharing capabilities using NIEMs common exchange standards, vocabulary, reusable data components and tools. |  |  | Design Costs Development Costs
| 3.0 Information Sharing Quality | Provides accurate, timely, complete, and relevant information to decision-makers across the broad spectrum of NIEM participating agencies. |  |  | Quality
| 4.0 Scalability | Provides a valuable framework, infrastructure and governance that is scalable beyond the current domains for other cross-government information exchange challenges. |  |  | Scalability
| 5.0 Standardization | The application of standard methodologies for scenario-based, information exchange mapping and modeling, and standards development improves efficiency and effectiveness. |  |  | Standardization
| 6.0 Interoperability | Creating new components in NIEM or migrating them from an existing standard to produce NIEM components facilitates cross-domain interoperability. |  |  | Interoperability
7
8
9
10

## 0.1 Dashboard (hidden)
0.0 Dashboard
Overview |  | Back to Overview
Initial Cost for NIEM vs XML by category (6.0)
Cost of NIEM vs XML as # of Exchanges Increase (6.0)

## 6.0 Appendix (hidden)
NIEM Cost Model v. 2.0 (Low Participation)
Appendix
Back to Overview
Appendix
| 1 | Analysis Initial - Sum of the amounts per resource type by taking the Level of Effort entered into 1.0 Activities tab and looks up the value in the 3.0 Cost Variables tab (Level of Effort table) and matches against the Exchange Complexity that is set in 2.0 Exchange Variables and multiplies the resource against the number of hours estimated and the hourly rate.
| 2 | Analysis Additional Exchange (Same Data) - Calculated total based on initial cost of that activity and the discount percentage given in the 1.0 Activities tab for reuse of the same data with a different exchange partner.
| 3 | Analysis Additional Exchange (New Data) - If there is a new exchange that is being created rather than reusing the previously defined exchange, then the costs to develop this new exchange is incurred but at a discount depending on the phase/step in the IEPD lifecycle.
| 4 | Total Cost to Build Exchange for the Year - Identifies the number of new exchanges and reused exchanges for the year and sums up the costs associated with all exchanges together for the year.
| 5 | Discount Factor (Existing IEPD) - If there is an existing IEPD out there that is the same exchange type.
| 6 | Discount Factor (Existing Elements) - If there are elements that are defined in this exchange that exist in the NIEM core, then there is a discount associated with the amount of elements that exist in the NIEM core.
7
8
9
10
11

## Sample Values (hidden)
0.0 Sample Values
| Cost Model (IEPD Exists, <50% Elements Exist) | Level of Effort |  | Same Data |  | New Data
| IEPD Phase | NIEM Exchange | Custom XML Exchange | NIEM Escalation | XML Escalation | NIEM Escalation | XML Escalation
| Scenario Planning | Medium | Medium | 25% | 50% | 100% | 100%
| Requirements Analysis | Medium | Medium | 0% | 50% | 100% | 100%
| Mapping and Modeling | Medium | High | 0% | 100% | 50% | 75%
| Building and Validating | Medium | High | 25% | 75% | 50% | 75%
| Assemble and Document | Low | None | 0% | 0% | 50% | 0%
| Publish IEPD | Low | None | 0% | 0% | 50% | 0%
| Project Variables | Value |  | Discount Factors | Value
| Number of Additional Systems | 1 |  | IEPD Exist? | Yes
| Number of Planned Additional Exchanges | 1 |  | Number of Elements New to NIEM | < 50%
| Complexity of exchange | Complicated
| NIEM Training Cost | 0
|  | NIEM Exchange |  |  | Custom XML Exchange
| IEPD Phase | Initial Exchange | Additional Exchange (Same Data) | Additional Exchange (New Data) | Initial Exchange | Additional Exchange (Same Data) | Additional Exchange (New Data)
Reoccurring Costs
| Scenario Planning | 70600 | 13250 | 70600 | 70600 | 35300 | 70600
| Requirements Analysis | 61200 | - | 61200 | 61200 | 30600 | 61200
| Mapping and Modeling | 32050 | - | 21838 | 62250 | 26250 | 44250
| Building and Validating | 92100 | 28550 | 46050 | 74350 | 74350 | 74350
| Assemble and Document | 20000 | - | 10000 | - | - | -
| Publish IEPD | 3000 | - | 1500 | - | - | -
| Subtotal Recurring Cost | 278950 | 41800 | 211188 | 268400 | 166500 | 250400
Discount Factors
| Existing IEPD | -96650 | -6500 | -73338 | - | - | -
| Adjustment for NIEM Element Existence | - |  |  | - | - | -
| Subtotal Discount Factors | -96650 | -6500 | -73338 | - | - | -
| Total Cost | 182300 | 35300 | 137850 | 268400 | 166500 | 250400
| Cost Model (IEPD Exists, >50% Elements Exist) | Level of Effort |  | Same Data |  | New Data
| IEPD Phase | NIEM Exchange | Custom XML Exchange | NIEM Escalation | XML Escalation | NIEM Escalation | XML Escalation
| Scenario Planning | Medium | Medium | 25% | 50% | 100% | 100%
| Requirements Analysis | Medium | Medium | 0% | 50% | 100% | 100%
| Mapping and Modeling | Medium | High | 0% | 100% | 50% | 75%
| Building and Validating | Medium | High | 25% | 75% | 50% | 75%
| Assemble and Document | Low | None | 0% | 0% | 50% | 0%
| Publish IEPD | Low | None | 0% | 0% | 50% | 0%
| Project Variables | Value |  | Discount Factors | Value
| Number of Additional Systems | 1 |  | IEPD Exist? | Yes
| Number of Planned Additional Exchanges | 1 |  | Number of Elements New to NIEM | > 50%
| Complexity of exchange | Complicated
| NIEM Training Cost | 0
|  | NIEM Exchange |  |  | Custom XML Exchange
| IEPD Phase | Initial Exchange | Additional Exchange (Same Data) | Additional Exchange (New Data) | Initial Exchange | Additional Exchange (Same Data) | Additional Exchange (New Data)
Reoccurring Costs
| Scenario Planning | 70600 | 13250 | 70600 | 70600 | 35300 | 70600
| Requirements Analysis | 61200 | - | 61200 | 61200 | 30600 | 61200
| Mapping and Modeling | 32050 | - | 21838 | 62250 | 26250 | 44250
| Building and Validating | 92100 | 28550 | 46050 | 74350 | 74350 | 74350
| Assemble and Document | 20000 | - | 10000 | - | - | -
| Publish IEPD | 3000 | - | 1500 | - | - | -
| Subtotal Recurring Cost | 278950 | 41800 | 211188 | 268400 | 166500 | 250400
Discount Factors
| Existing IEPD | -96650 | -6500 | -73338 | - | - | -
| Adjustment for NIEM Element Existence | -10900 | - | -5450 | - | - | -
| Subtotal Discount Factors | -107550 | -6500 | -78788 | - | - | -
| Total Cost | 171350 | 35300 | 132400 | 268400 | 166500 | 250400